## Slide 1
skyforce / RSEE4
2010/10/14
Weekly Report

## Slide 2: CCTv3 Improvement Research - Status
Progress
  AUO 11307 Platform 9/27~10/15
    Color engine toolkit integrated 10/4~10/8
Problem
  UI移植
Future Plan
  AUO 11307 Platform 9/27~10/15
    Adjust verification 10/11~10/15
  Auto Adjust Color Database 10/18~11/05
    Luminance Mapping 10/18~10/19
    Auto toolkit 10/20~10/26
    Color Database 10/27~11/2
    SOP 11/3~11/05
  Dim Grey Fix: Find Reasonable Target White 11/08~12/24
    Meet CCT criteria 11/08~11/19
    Meet eye inspect 11/22~12/17
    Workbook 12/20~12/24

## Slide 3
 |  |  |  | 2010 Sep |  |  |  | 2010 Oct |  |  |  | 2010 Oct |  |  | 
List | Item | Start | End | 9/6 | 9/13 | 9/20 | 9/27 | 10/4 | 10/11 | 10/18 | 10/25 | 11/1 | 11/8 | 11/15 | 11/22
CCTv3 | 下視角亮度差 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | Dim Grey Fix | 11/8 | 12/24 |  |  |  |  |  |  |  |  |  |  |  | 
 | -低灰階異色threshold實驗 | 11/8 | 11/19 |  |  |  |  |  |  |  |  |  |  |  | 
 | -最適Dim Target White自動產生 | 11/22 | 12/17 |  |  |  |  |  |  |  |  |  |  |  | 
 | -Workbook | 12/20 | 12/24 |  |  |  |  |  |  |  |  |  |  |  | 
 | Non-stable CCT (B116XW03) |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 | -面板特性解析 |  |  |  |  |  |  |  |  |  |  |  |  |  | 
AUO-11307 Platform | HSV manual-adjustment revised | 9/27 | 10/1 |  |  |  |  |  |  |  |  |  |  |  | 
 | color engine toolkit integrated | 10/4 | 10/8 |  |  |  |  |  |  |  |  |  |  |  | 
 | Sharpness/CM/HSV/CCT verification | 10/11 | 10/15 |  |  |  |  |  |  |  |  |  |  |  | 
Color Database | color engine auto-toolkit | 9/20 | 10/8 |  |  |  |  |  |  |  |  |  |  |  | 
 | -gamut mapping | 10/18 | 10/19 |  |  |  |  |  |  |  |  |  |  |  | 
 | -embedded in CM/HSV auto-toolkit | 10/20 | 10/26 |  |  |  |  |  |  |  |  |  |  |  | 
 | color database | 10/27 | 11/2 |  |  |  |  |  |  |  |  |  |  |  | 
 | color engine SOP | 11/3 | 11/5 |  |  |  |  |  |  |  |  |  |  |  |